## Slide 1: SDMX Implementation Checklist to Manage a SDMX Project

## Slide 2: Introduction
A guideline to help approach a project in the right order for the best quality outcome
Not meant to be prescriptive. It is a guideline that should be customised
Compiled from:
  what has worked in SDMX implementations
  project management best practices
Project milestones are at the end of each “stage”

## Slide 3: Top-level stages
Used GSBPM v5.0 at high-level to check gaps
SDMX implementation checklist stages
SPECIFY NEEDS
PLAN AND ORGANISE
DESIGN
BUILD
PROCESS/
ANALYSE
DISSEMINATE
EVALUATE

## Slide 4
SPECIFY NEEDS
PLAN AND ORGANISE
DESIGN
BUILD
PROCESS/
ANALYSE
DISSEMINATE
EVALUATE
Describe needs;
Get approval
Identify stakeholders
* Check for existing content
Kick-off meeting
Project proposal
** Project governance
** Maintenance agreement; Ownership group structure;
ToR
Communication and consultation planning
Check the SDMX Global Registry
Check SDMX Content-oriented Guidelines (COG)
Consult with SDMX Statistical Working Group (SWG)
Check the guidelines “Governance of Commonly Used SDMX Metadata Artefacts“

## Slide 5
PLAN AND ORGANISE
DESIGN
BUILD
PROCESS/
ANALYSE
DISSEMINATE
EVALUATE
SDMX training for team
Project roadmap and work breakdown
Collaboration platform and issue log
SDMX project templates
Define pilot phase details and participants
Describe needs;
Get approval
Identify stakeholders
Check for existing content
Kick-off meeting
Project proposal
Project governance
Maintenance agreement; Ownership group structure;
ToR
Communication and consultation planning
SPECIFY NEEDS

## Slide 6
SPECIFY NEEDS
PLAN AND ORGANISE
DESIGN
BUILD
PROCESS/
ANALYSE
DISSEMINATE
EVALUATE
Describe data flows and architectures
Decide which artefacts to reuse
* Design “core” artefacts
* Design supporting artefacts
Execute pilot phase 1: Content review
Describe needs;
Get approval
Identify stakeholders
Check for existing content
Kick-off meeting
Project proposal
Project governance
Maintenance agreement; Ownership group structure;
ToR
Communication and consultation planning
SDMX training for team
Project roadmap and work breakdown
Collaboration platform and issue log
SDMX project templates
Define pilot phase details and participants
* Design principles covered in the presentation:
“How to model a statistical domain for data exchange in SDMX”
Data Flows; Concept Scheme; DSDs; Codelists.
Provision Agreements; Constraints; Category Schemes…
SDMX Content-oriented Guidelines:
Cross-domain Code Lists
Cross-domain Concepts
SDMX Glossary
Registries
Reuse of existing Code Lists

## Slide 7
SPECIFY NEEDS
PLAN AND ORGANISE
DESIGN
BUILD
PROCESS/
ANALYSE
DISSEMINATE
EVALUATE
Check matrix contents matches COG
Create artefacts in registry
Develop mappings
* Check artefacts conform to technical standards
Implementation and usage guidelines
Create tech. pilot review material
Describe data flows and architectures
Decide which artefacts to reuse
Design “core” artefacts
Design supporting artefacts
Execute pilot phase 1: Content review
Describe needs;
Get approval
Identify stakeholders
Check for existing content
Kick-off meeting
Project proposal
Project governance
Maintenance agreement; Ownership group structure;
ToR
Communication and consultation planning
SDMX training for team
Project roadmap and work breakdown
Collaboration platform and issue log
SDMX project templates
Define pilot phase details and participants
* Check the SDMX Technical Specifications and XML schemas
Notes: Check matrix…: Show the National Accounts matrix
Develop mappings: Mention SDMX StructureSets

## Slide 8
SPECIFY NEEDS
PLAN AND ORGANISE
DESIGN
BUILD
PROCESS/
ANALYSE
DISSEMINATE
EVALUATE
Execute pilot phase 2:
Technical review
Test exchange systems
Compile issue log. Consult with TWG for technical issues
Review issue log
Check matrix contents matches COG
Create artefacts in registry
Develop mappings
Check artefacts conform to technical standards
Implementation and usage guidelines
Create pilot review material
Describe data flows and architectures
Decide which artefacts to reuse
Design “core” artefacts
Design supporting artefacts
Execute pilot phase 1: Content review
Describe needs;
Get approval
Identify stakeholders
Check for existing content
Kick-off meeting
Project proposal
Project governance
Maintenance agreement; Ownership group structure;
ToR
Communication and consultation planning
SDMX training for team
Project roadmap and work breakdown
Collaboration platform and issue log
SDMX project templates
Define pilot phase details and participants

## Slide 9
SPECIFY NEEDS
PLAN AND ORGANISE
DESIGN
BUILD
PROCESS/
ANALYSE
DISSEMINATE
EVALUATE
Execute pilot phase 2:
Technical review
Test exchange systems
Compile issue log. Consult with TWG for technical issues
Review issue log
Check matrix contents matches COG
Create artefacts in registry
Develop mappings
Check artefacts conform to technical standards
Implementation and usage guidelines
Create pilot review material
Describe data flows and architectures
Decide which artefacts to reuse
Design “core” artefacts
Design supporting artefacts
Execute pilot phase 1: Content review
Describe needs;
Get approval
Identify stakeholders
Check for existing content
Kick-off meeting
Project proposal
Project governance
Maintenance agreement; Ownership group structure;
ToR
Communication and consultation planning
SDMX training for team
Project roadmap and work breakdown
Collaboration platform and issue log
SDMX project templates
Define pilot phase details and participants
Publish artefacts in production
Publish maintenance and information
Switch from project governance to maintenance agreement
Provide support and training to implementors

## Slide 10
SPECIFY NEEDS
PLAN AND ORGANISE
DESIGN
BUILD
PROCESS/
ANALYSE
DISSEMINATE
EVALUATE
Execute pilot phase 2:
Technical review
Test exchange systems
Compile issue log. Consult with TWG for technical issues
Review issue log
Check matrix contents matches COG
Create artefacts in registry
Develop mappings
Check artefacts conform to technical standards
Implementation and usage guidelines
Create pilot review material
Describe data flows and architectures
Decide which artefacts to reuse
Design “core” artefacts
Design supporting artefacts
Execute pilot phase 1: Content review
Describe needs;
Get approval
Identify stakeholders
Check for existing content
Kick-off meeting
Project proposal
Project governance
Maintenance agreement; Ownership group structure;
ToR
Communication and consultation planning
SDMX training for team
Project roadmap and work breakdown
Collaboration platform and issue log
SDMX project templates
Define pilot phase details and participants
Publish artefacts in production
Publish maintenance and information
Switch from project governance to maintenance agreement
Provide support and training to implementors
Gather evaluation inputs
Conduct project evaluation
Implement the evaluation actions
Provide feedback to the SDMX SWG

## Slide 11: In conclusion
Using the checklist can:
  Save you time in deciding how to structure the project
  Prevent unneeded work and backtracking by ensuring that the project is approached in the correct order,
  Help to get the right people on board at the right time
  Indicate which documents and material to consult for the best outcome
Not a methodology, based on lessons learned
  (ok, also a bit of project management methodology)
Remember! The checklist is a guideline only and should be adapted
The checklist is in “draft” status; the SDMX SWG welcomes feedback on it

## Slide 12: Thank you! Questions?
Daniel.SURANYI@ec.europa.eu
David.Barraclough@oecd.org
SDMX Basics

## Slide 13
SPECIFY NEEDS
PLAN AND ORGANISE
DESIGN
BUILD
PROCESS/
ANALYSE
DISSEMINATE
EVALUATE
SDMX training for team
Project roadmap and work breakdown
Collaboration platform and issue log
SDMX project templates
Define pilot phase details and participants
Describe data flows and architectures
Decide which artefacts to reuse
Design new “core” artefacts
Design supporting artefacts
Execute pilot phase 1: Content review
Check matrix contents matches COG
Create artefacts in registry
Develop mappings
Check artefacts conform to technical standards
Implementation and usage guidelines
Create pilot review material
Execute pilot phase 2:
Technical review
Test exchange systems
Compile issue log. Consult with TWG for technical issues
Review issue log
Publish artefacts in production
Publish maintenance and information
Switch from project governance to maintenance agreement
Provide support and training to implementors
Gather evaluation inputs
Conduct project evaluation
Implement the evaluation actions
Provide feedback to the SWG
Describe needs;
Get approval
Identify stakeholders
Check for existing content
Kick-off meeting
Project proposal
Project governance
Maintenance agreement; Ownership group structure;
ToR
Communication and consultation planning