## Slide 1: The COVID-19 pandemic: Potential adjustments in census questionnaires
2nd November 2021
Owusu Kagya
Ghana Statistical Service

## Slide 2: Outline
  Introduction
  Anticipated challenges due to Covid-19
  Changes in the 2021 PHC plans
  Potential adjustments to census questions due to Covid-19

## Slide 3: Introduction
Goal of the 2021 PHC
Initial plans for the 2021 PHC
  Cartographic mapping: completed pre-COVID
  Recruitment and training of Field staff: online application with in-person screening
  Duration of the enumeration/data collection: 7 days of listing and 14 days of enumeration
  Method of enumeration/ data collection: in-person
Notes: Four levels of training – MT completed pre-Covid; all others completed post Covid

## Slide 4: Anticipated Challenges due to Covid-19 (1/2)
Information collected
  No change in the instruments and the amount of information collected
Loss of periodicity (shift in the census year):
  Census postponed from 2020 to 2021
Changes in the season of enumeration:
  Census Night rescheduled to 27th June
  Data collection conducted during the rainy season

## Slide 5: Anticipated Challenges due to Covid-19 (2/2)
Low response rates
  In anticipation of COVID-19 related hesitancy, enumerators were provided PPEs and trained on maintaining social distance, and
  Publicity, education and advocacy used to raise awareness of the importance of census data for targeted policies such as for pandemic response

## Slide 6: Changes in the PHC Plans due to COVID-19 (1/2)
Method of data collection
  In-person with COVID-19 protocols (mask wearing and 2m social distance between enumerators and respondents)
Duration for training (extended); listing and enumeration (unchanged)
Census publicity/communication:
  Census webinars for stakeholders
  Live streaming of in-person publicity, education and advocacy events with limited participants
  Social media public education campaign
Notes: Imperative to assess the changes in plan in light of the conduct of a MAIDEN FULLY technology driven census

## Slide 7: Changes in the PHC Plans due to COVID-19 (2/2)
New activities introduced because of COVID-19
  Virtual self-learning, virtual training for all levels of trainers to complement face-to-face training
  Virtual technical working group meetings
  Virtual meetings with regional and district teams

## Slide 8: Potential adjustments to census questions due to Covid-19?
Additional guidance to support respondents in answering questions in the context of the pandemic
    Age
    Fertility
    Mortality
    Internal migration
    Emigration
    Economic activities
    School attendance
Notes: Adjustment to improve relevance and quality of census data

## Slide 9: Thank You Email: kagya.owusu@statsghana.gov.gh