**JOINT NATIONAL ACTION PLAN: PHILIPPINES**

**Introduction**

This Joint National Action Plan is based on our analysis of the status of the available data by domain for the Ministerial Declaration and Region-Wide Sets of Indicators. Our specific objectives are focused on the following: a) indicators that are not yet generated but the data are available; and b) coming up with an action plan for those indicators that have no data at present.

**Overall Goal:** Improve quality and availability of gender-related statistics and indicators to support evidence-based policy making and programming for gender equality and empowerment of women

| **SPECIFIC OBJECTIVES / RESULT** | **OUTPUTS** | **ACTIVITIES** | **STAKEHOLDERS** | **ASSUMPTIONS** | **TIMEFRAME** |
| --- | --- | --- | --- | --- | --- |
| 1. To generate the “indicators not produced but data are collected” in the Report for the Region-wide Review of the Core Set of Gender Indicators for Asia and the Pacific
 | 1. Indicators that are not currently computed but data are collected available
 | * + 1. Issuance of circular to all concerned agencies on the Ministerial Declaration, the Global and Regional Core Sets of Indicators and the need for the data monitoring
		2. Review global and regional core set indicators by domain
		3. Compute the indicators that are available from existing PSA censuses and surveys
		4. Collect admin-based data inputs from concerned agencies
		5. Compute indicators based from the admin-based data inputs
		6. Present indicators from admin-based results to relevant source agencies for them to appreciate the relevance of their admin-based data
 | Concerned agencies PSA PCW International organizations  | Delay in submission of admin-based data  | October – December 2015  |
| 1. To generate the Social Protection Index (SPI), by sex within the next three years
 | 1. SP statistical framework
2. SPI methodology
3. SPI indicators
 | * + 1. Conduct of coordination meetings and discussions with IAC-Social Protection on the statistical framework
		2. Review of related literature and ADB methodology
		3. Gathering of data inputs within PSA and with SSS, GSIS, PHIC, DSWD and other relevant agencies
		4. Develop methodology and computational procedures
		5. Pilot SPI methodology and computational procedures
		6. Presentation to IAC-SP
		7. Finalize SP methodology and computational procedures
		8. Presentation to PSA Board for approval
		9. Integration of the SPI in the Philippine Statistics Development Plan *(long-term)*
 | Member agencies of IAC-SP Social protection agencies, e.g. SSS, GSIS, PHIC, DSWD, among othersPCW, NEDA-Multi-Sectoral Committee on International Human Development Commitments International organizations | Data support (administrative data) from social protection agencies Availability of resources: 1. Human resource
2. Expertise
3. Funding
 | Year 1 – Activities 2.1.1-2.1.3 Year 2 – Activities 2.1.4-2.1.6 Year 3 – Activities 2.1.7-2.1.8 |
| 1. To generate gender indicators for the Ministerial Declaration from the establishment data
 | * 1. Reviewed Census of Philippine Business and Industries (CPBI)
	2. Reviewed List of Philippine Business and Industries
 | * + 1. Review and revise forms for the CPBI and list of Philippine Business and Industries to ensure gender dimension
		2. Pre-test/pilot of the revised forms
		3. Review budget implications
		4. Present to Inter-Agency Committee concerning establishments
		5. Budget preparation and allocation
		6. Implementation in the data collection, processing, analysis and dissemination
 | PSA, PCW, international organizations, women CSOs  | Human resource and expertise are available to support the initiative Budget availability Risk: Lack of awareness of private sector entities on gender equality initiatives  | Year 1 – Activities 3.1.1-3.1.3Year 2 – Activities 3.1.4-3.1.5Year 3 – Activity 3.1.6  |
| 1. To improve the availability and sex-disaggregation in administrative based data
 | 1. Improved selected admin-based data
 | * + 1. Review and revise related PSA resolutions and policies on the production of gender statistics
		2. Presentation to the PSA Board for approval
		3. Re-issuance of approved PSA resolutions
		4. Monitoring of agency compliance to PSA resolutions
		5. Strengthening the mechanism for gender statistics (c/o PSA)
		6. Training of data producers and data users on gender statistics
		7. Advocacy on the use of gender statistics
		8. Budget preparation and allocation
 | PSA, PSRTI and PCW Concerned agencies and local experts  | Cooperation of concerned data-producing agencies  | Year 1 – Activities 4.1.1-4.1.3; preparation to implement Activity 4.1.4Year 2 – Implementation of Activities 4.1.4, 4.1.**5**, 4.1.6, 4.1.7 and 4.1.8 Year 3 – Activities 4.1.4, 4.1.6, 4.1.7 and 4.1.8  |
| 1. To work towards increasing availability of data on peace and security and disaster risk reduction and environment

  | * 1. Action Plan to make data on peace and security and disaster and environment available
 | * + 1. Assessment of existing data from the concerned agencies as sources for generating the indicators
		2. Identify data gaps and problems in collecting information needed for the indicators and to determine whether the data can be collected through surveys or from administrative reporting
		3. Conduct of meetings with PSA, concerned agencies and inter-agency committees (e.g. NSC-NAPWPS, NDRRMC) to identify possible solutions and to seek endorsement for budgetary support
		4. Come up with plans and proposed budget for data collection, processing, analysis and advocacy for presentation to the PSA Board and concerned IACs
 | Concerned agencies Inter-Agency Committees/Councils PSA PCW  | Willingness of concerned agencies to participate in the formulation and implementation of the action plan Resources will be made available.  | Year 1 – Activities 5.1.1 and 5.1.2 Year 2 – Activities 5.1.3 and 5.1.4   |

For Inclusion:

1. SDG Indicators concerning gender
2. Results of EDGE pilot
3. Review of the census/survey instruments
4. Elevating the IAC-GS to TC-GS