## Slide 1: Culture Satellite Account : The Road Ahead
UIS Culture Satellite Account Experts Meeting (CSAEM)
4-6th November 2015
José Pessoa, Programme Specialist,
Head of Culture Statistics

## Slide 2: 3 products to develop
International Recommendations for Culture Satellite Account (CSA) 201X
Culture Satellite Account (CSA): Compilation Guide 201X
International Recommendations for Culture Statistics 201X

## Slide 3: General Plan
Year | Year
2015 | Consultant Study; CSA Experts Meeting
2016 | Preliminary Draft 1 CSA; Limited Consultations;
2017 | Review CSA Technical Advisory Group (TAG); Preliminary Draft 2 CSA; Global Consultations;
2018 | Final Draft CSA; Review CSA Technical Advisory Group (TAG)/ISWGNA Submission to UNSC (November)
2019 | Adoption at UNSC (March); Adoption at UNESCO General Conference (November); Produce International Recommendations for Culture Statistics Preliminary Draft;
2020 | Produce International Recommendations for Culture Statistics Preliminary Final Document;
2021 | Produce CSA Compilation Guide Preliminary Draft
2022 | Produce CSA Compilation Guide Final Document

## Slide 4: CSA 2016
Establish the UIS CSA Technical Advisory Group (CSA TAG)
  Guide the work of the CSA
  Composed of key partners and experts
  Face to face meeting as necessary
  Virtual meetings as necessary
Preliminary Draft 1 CSA
Limited consultations
  with whom?

## Slide 5: CSA TAG
Composition of CSA TAG
  UIS (Chair)/UIS CSA Consultant?
  UNSD
  OECD
  Eurostat
  IMF?
  Asia/Africa/Latin America Organizations?
  Country representatives? (how many?)
  Others?

## Slide 6: CSA 2017
Review by CSA TAG and ISWGNA
Preliminary Draft 2
Global Consultations
  Led by UIS and UNSD?
  Member States (National Statistical Office and Ministry of Culture)
  Other stakeholders?
  In what form? Electronic only? Regional consultation meetings?

## Slide 7: CSA 2018
Final Draft
Review by CSA TAG and ISWGNA
Preparation of Final CSA Document
  Submit to UNSC by end November

## Slide 8: CSA 2019
CSA tabled at UNSC for adoption (March)
CSA tabled at UNESCO General Conference for information (November)
Develop UIS strategy to support member states in CSA implementation

## Slide 9: 2019-2022
Produce International Recommendations for Culture Statistics
Produce CSA Compilation Guide

## Slide 10
Is this time table realistic?
Is there anything missing?
How much does this cost?

## Slide 11
Thank you!